Repairs to timber Floor Deck/strutting and making good of previous repairs to access hatches and skirtings/wall. Refer to item 5 in the resolution report dated 1/11/19.
This schedule has been compiled by Brian Hitchenor t: 01604 589581
This schedule is to be read in line with the Schedule of Works Standard Preliminaries contained in Schedule 7 of the NHBC Contractors Framework Agreement
SCOPE OF WORKSThe works comprise reinstatement works to incorrectly fitted floor access hatches and installation of timber 'strongbacks' from front to back in the rear bedroom and making good of previous repairs to skirtings in rear bedroom.
This schedule is be read in conjunction with - NHBC investigation report dated 1 November 2019

RISKSConsideration is likely but not exclusively to include the following:THIS SCHEDULE IS ISSUED FOR COSTING/SCOPE OF WORKS PURPOSES ONLY. THE CONTRACTOR IS RESPONSIBLE FOR ALL ASPECTS RELATING TO HEALTH AND SAFETY.
GENERALThe RWC is advised that the works will take place in: occupied premises
TEMPORARY PROTECTION AND CLEANING
Temporary protection - internally; to include securing with tape or temporary fixings; periodical taking up and relaying/adapting/fixing (including on a daily basis if required) ; removal and storage for reuse on completion and making good disturbed or marked surfaces, including decoration where necessary

Z0908010201
Temporary protection to floors, dustsheetsFF hallway 4 sq.m;Rear bedroom 12 sq.m
16.00m2

Z0908010210
Temporary protection to floors and walls; Correx Protecta Multiguard roll-out sheet; taping joints and perimeter; removal on completion; 350 gsmGF Hallway 5sq.m
5.00m2

Z0908010208
Temporary protection to stairs; Correx Protecta stair tread and riser protection; trimming units to suit; taping joints; removal on completion; 200 x 200mm x 1.20m long x 2mm thick; to suit 13 nr riser unit
1.00
Nr

CLEANING
Z0908010806
Professional cleaning following major repair works - per individual room.
1.00
Item
WELFARE UNITS

Z0908010703
Portable Hot wash toilet unit; portable toilet serviced weekly; delivered to site, maintained through hire period, collected on completion; initial two week minimum hire basis; hire period, one week rate
2.00
Week
Disposal of debris( Note - disposal of excavated material in foundations, underpinning and drainage works included in measured items)

Z0906030110
Skip hire - 2yd3
0.50
Week
REMEDIAL WORKS
REPLACE TIMBER FLOOR DECK
FLOORS
Z0302061501
Take up existing fitted carpet and underlay; store and protect; relay on completion of remedial worksFF landing 4 sq.m;Rear bedroom 12 sq.m
16.00
m2

Z0302060902
Cut out sections of chipboard floor deck (for localised inspection or repair) back to nearest joist ensuring all areas of damaged tongued and grooved joints are fully removed. Provide and securely fix min 50 x 75mm softwood noggin to all sides of area removed. Provide and fix new section of 22mm Type P5 chipboard to match existing. Fix using adhesive between joist and decking and screws 75mm long 10 gauge countersunk wood screws to all four perimeter noggins at 150mm max c/s. Additionally, screw fix the existing deck at the perimeter of the new section at 150mm max c/s. Installation and adhesive to be to used to fix all boards down and glued joints to manufacturer's recommendation.Works are to the rear bedroom, running from front to back along a central area to enable the fitting of strutting/strongbacks and to remove and replace the defective access hatches previously formed by the builder's previous works.
3.00
m2

Z0202020101
Install 75mm x 50mm solid timber strutting, for no less than 75% of the depth of the joist. Strutting should not project beyond the top and bottom edges of the joists. At the end of each run of strutting the last joist should be firmly blocked to the wall. Work is to ensure that the 'strongback' struts to the Eco joists are preventing significant movement/flex of the joists. The struttIng works/strongback works must run from front to back in the rear bedroom and lap with the previous works to the landing area.
6.00
m
FLOORS

[bookmark: _GoBack]Z0302060810
Install additional screw fixings to chipboard and plywood floor decks at 200-300mm c/s to board perimeters, 400-500mm c/s on intermediate supports, countersunk screw length to be 2.5 times the thickness of the board, screw heads not to protrude above the floor surface. To rear bedroom/landing.
14.00
m2
WINDOWS, DOORS AND TIMBER JOINERY
INTERNAL JOINERY
Skirtings
Z0206030217

EXTRA - gloss paintwork to skirting to match the existing, knot, stop, fill, rub down, 1 Nr coat primer, 1 Nr coat undercoat, 1 Nr coat topcoat, OR in full accordance with the paint manufacturers recommendations if different to above. Girth not exceeding 200mm. To previous incomplete repairs to the rear bedroom.
3.00
m

WALLS - PAINT AND COVERINGS
Emulsion to walls, vinyl silk, wash down, stop in and rub down.
Z0302040105
1 Nr full coat, width exceeding 300mm-To the previous incomplete repairs to the partition area (see skirting item above).
6.00
m2
### END OF SCHEDULE ###

